## Dashboard
Event Budget Planner
Formula-driven portfolio workbook - edit the Data sheet to update every KPI and chart
Allocated budget total |  | Actual cost total | Achievement
367200 |  | 351522 | 95.73%
Category | Allocated budget | Actual cost
Venue | 118800 | 114696
Food | 122400 | 120118.5
Media | 126000 | 116707.5
Synthetic portfolio data. Replace rows on the Data sheet; formulas and chart update automatically.

## Data
Date | Cost group | Category | Allocated budget | Actual cost | Variance | Achievement | Status
2026-01-01 | Cost group 01 | Venue | 25650 | 26419.5 | 769.5 | 103% | Missed
2026-02-01 | Cost group 02 | Food | 26550 | 22567.5 | -3982.5 | 85% | Met
2026-03-01 | Cost group 03 | Media | 27450 | 25254 | -2196 | 92% | Met
2026-04-01 | Cost group 04 | Venue | 28350 | 28066.5 | -283.5 | 99% | Met
2026-05-01 | Cost group 05 | Food | 29250 | 31005 | 1755 | 106% | Missed
2026-06-01 | Cost group 06 | Media | 30150 | 26532 | -3618 | 88% | Met
2026-07-01 | Cost group 07 | Venue | 31050 | 29497.5 | -1552.5 | 95% | Met
2026-08-01 | Cost group 08 | Food | 31950 | 32589 | 639 | 102% | Missed
2026-09-01 | Cost group 09 | Media | 32850 | 27594 | -5256 | 84% | Met
2026-10-01 | Cost group 10 | Venue | 33750 | 30712.5 | -3037.5 | 91% | Met
2026-11-01 | Cost group 11 | Food | 34650 | 33957 | -693 | 98% | Met
2026-12-01 | Cost group 12 | Media | 35550 | 37327.5 | 1777.5 | 105% | Missed